# FinTrack Production Readiness Assessment

Document owner: Engineering
Version: 1.0
Status: Draft for review
Scope: What must be done, in what order, and what it will cost for FinTrack to be safely usable by real-world end users.

## 1. Executive summary

FinTrack is a feature-complete personal finance application. The product surface is broad: linked bank accounts, transaction sync, budgets, goals, bills, debt planning, AI analysis, an AI assistant, savings vault, tax organizer, household accounts, web push notifications, and a native mobile wrapper for Android and iOS.

The application is not yet ready for public end users in its current state. The functional gaps are smaller than the operational, security, and compliance gaps. Everything in this document is achievable, but it requires a structured programme of work, not a single release.

This assessment classifies work into four priority tiers:

| Tier | Definition | Indicative cost |
| --- | --- | --- |
| P0 | Must exist before any real users | USD 21,000 - 38,000 |
| P1 | Required for a controlled public launch | USD 13,000 - 25,000 |
| P2 | Required within 12 months of launch | USD 9,000 - 18,000 |
| P3 | Recommended growth and resilience work | USD 6,000 - 14,000 |

Estimated total one-time build: USD 49,000 - 95,000
Estimated ongoing monthly operating cost: USD 850 - 3,100 (details in section 10)

Readiness score today: ~4 out of 10 for general consumers; ~6 out of 10 for a small closed beta.

## 2. Readiness scorecard

Each domain is scored 0 - 5 against what a public fintech product must meet.

| Domain | Score | Summary |
| --- | --- | --- |
| Product and UX completeness | 4 / 5 | Broad feature set; gaps in empty states, error recovery, and help |
| Core security | 4 / 5 | Strong foundations (bcrypt, AES-GCM, JWT) plus rate limiting, CSP/HSTS headers. Missing audit log, secret rotation, DDoS protection |
| Compliance and legal | 1 / 5 | No privacy policy, terms, data processing agreements, or financial disclosures |
| Infrastructure and reliability | 2 / 5 | Single region, no backups, no monitoring, no alerting, no SLOs |
| Data and privacy | 2 / 5 | Retention policy absent, no data export or deletion automation, weak consent flows |
| Bank connectivity | 3 / 5 | Plaid integrated and encrypted. Webhook sync, reconciliation, and disaster recovery missing |
| AI reliability | 3 / 5 | Local fallback engine exists. No PII redaction, no usage budgets, no hallucination guardrails |
| Mobile store readiness | 2 / 5 | APK builds. No signed release builds, no app store assets, no privacy nutrition labels |
| Monitoring and support | 1 / 5 | No error tracking, no logs, no support channel, no user feedback loop |
| Accessibility | 2 / 5 | Basic aria labels. No WCAG audit, no contrast/FA audits |
| Performance | 3 / 5 | Fast in common paths. No CDN, no load testing, no pagination on large datasets |
| Testing | 2 / 5 | No automated test suite, no CI test stage, no load tests, no staging environment |

## 3. P0: Required before any real users

### 3.1 Security hardening

Current state: bcrypt (cost 12), AES-256-GCM token encryption, JWT with HttpOnly cookies, NextAuth CSRF, email verification, Zod input validation.

Gaps and required work

- Rate limiting on every authentication and AI endpoint. Done. An in-memory limiter (lib/rate-limit.ts) now throttles register, forgot-password, verify-email, reset-password, change-email, change-password, chat, and intelligence endpoints.

  - Remaining: scale to an external store (Upstash Ratelimit or Vercel edge rate limiting middleware) for multi-region deployments.

  - Effort: 2 - 4 days (partially done).

- Security headers and DDoS protection. Headers done. CSP, HSTS, X-Content-Type-Options, X-Frame-Options, Referrer-Policy, and Permissions-Policy set in next.config.js.

  - Remaining: enable Vercel WAF or Cloudflare in front.

  - Effort: 1 - 3 days (partially done).

- Secrets management and rotation. ENCRYPTION_KEY, NEXTAUTH_SECRET, Plaid secrets, SMTP credentials, and the Anthropic key must be in a vault (Vercel Env / Doppler / AWS Secrets Manager), with a documented rotation runbook. Add a KMS-backed key versioning plan so a rotated encryption key can re-encrypt stored Plaid tokens.

  - Effort: 3 - 5 days.

- Audit log. Record security-relevant events: login, failed login, password change, email change, account link, account unlink, data export, settings change.

  - New AuditLog table + middleware in write paths.

  - Effort: 4 - 6 days.

- Session hardening. Shorten JWT expiry, add sliding sessions, and revoke sessions on password change. Consider server-side session store.

  - Effort: 2 - 4 days.

- Penetration test. Engage a third party after hardening is complete (USD 3,000 - 15,000 depending on scope).

### 3.2 Compliance and legal (non-negotiable before launch)

Engage legal counsel for all of the following. Template costs assume a startup-friendly fintech law firm.

- Terms of Service (USD 1,500 - 4,000).

- Privacy Policy that documents data collected, processors, purpose, retention, and user rights under GDPR/CCPA (USD 1,500 - 4,000).

- Cookie and consent banner with legitimate-interest settings (USD 500 - 1,500 implementation + template licence).

- Data Processing Agreement with cloud and AI providers (USD 500 - 1,500).

- Data retention schedule and deletion policy, with automated enforcement (GDPR Article 5(1)(e)) (USD 2,000 - 4,000 engineering).

- Financial services disclosures. The app analyses finances but does not move money or give regulated advice. Still required: disclaimers that FinTrack is not a bank, not a financial adviser, and that AI output is informational. Confirm with counsel whether a money-services or e-money licence is triggered in each launch market. For most markets, an informational analysis tool does not require a licence, but legal confirmation is mandatory before launch (USD 1,000 - 5,000 opinion).

- AI output compliance. Provide a model card / disclosure that AI analysis is generated and may be wrong; add “not financial advice” wording to all AI surfaces (small).

### 3.3 Infrastructure, backups, and monitoring

- Production database on a managed Postgres (Neon/Supabase/RDS) with:

  - Point-in-time recovery enabled.

  - Automated daily backups with retention and restore drill (monthly).

  - Read replica if growth requires it.

  - Cost: from USD 19 - 120 / month on Neon/RDS.

- Uptime and error monitoring.

  - Sentry (error tracking, front and back end) - Free tier to USD 26 / month.

  - Vercel analytics + uptime checks, or Betterstack/UptimeRobot - Free to USD 40 / month.

  - Structured logs: Vercel Logs or Axiom - Free to USD 25 / month.

- SLOs and runbooks. Define 99.5% availability target, alert thresholds for sync failures, Plaid outage handling, AI outage fallback.

  - Effort: 3 - 5 days.

- Staging environment. A second Vercel project + database that mirrors production for testing migrations and deploys.

  - Cost: database from USD 19 / month; minimal additional hosting.

- Deployment guardrails. Enforce CI checks (typecheck, lint, tests) before merge; add a database migration review step for prisma migrate.

### 3.4 Data and privacy engineering

- Data export (GDPR Article 20). Export all user data as JSON/CSV (effort: 3 - 5 days).

- Account deletion. Hard-delete flow with cascading cleanup of Plaid items (via item/remove), push subscriptions, receipts, and cached AI insights (effort: 3 - 5 days).

- Right-to-erasure automation for unverified accounts after a retention window.

- PII handling review. Ensure AI prompts receive only necessary transaction fields; add prompt-level redaction and an option to disable AI processing (effort: 2 - 4 days).

### 3.5 P0 cost summary

| Item | Effort | Cost |
| --- | --- | --- |
| Rate limiting | 2 - 4 days | USD 800 - 1,600 |
| Security headers + WAF | 1 - 3 days | USD 400 - 1,200 |
| Secrets management + rotation runbook | 3 - 5 days | USD 1,200 - 2,000 |
| Audit log | 4 - 6 days | USD 1,600 - 2,400 |
| Session hardening | 2 - 4 days | USD 800 - 1,600 |
| Penetration test | external | USD 3,000 - 15,000 |
| Legal: ToS + Privacy + DPA + disclosures | external | USD 3,500 - 12,000 |
| Cookie consent | 2 - 3 days | USD 800 - 1,200 |
| Data retention + deletion + export + erasure | 8 - 12 days | USD 3,200 - 4,800 |
| AI prompt redaction + disclosures | 2 - 4 days | USD 800 - 1,600 |
| Managed DB + backups + monitoring + logging | 4 - 6 days + infra | USD 1,600 - 2,400 + ~USD 100 - 180/month |
| Staging environment + CI guardrails | 3 - 5 days | USD 1,200 - 2,000 |

P0 subtotal: approximately USD 19,000 - 47,000 (engineering USD 14,000 - 25,000 plus external legal and security USD 6,500 - 27,000).

## 4. P1: Required for a controlled public launch

### 4.1 Testing

There is currently no automated test suite. Before public launch you need:

- Unit tests for the AI analysis engine, currency utilities, categorization rules, and encryption/decryption. Vitest + Testing Library (5 - 8 days).

- API integration tests for auth, transactions, budgets, goals, Plaid exchange/sync (mocked Plaid), and chat (7 - 12 days).

- E2E smoke tests for the critical journeys: register, verify email, link a bank, view dashboard, add a manual transaction, chat (Playwright) (5 - 8 days).

- CI pipeline running typecheck, lint, unit, and integration tests on every PR (2 - 3 days).

- Load test of the dashboard and intelligence endpoints with k6 to confirm the serverless configuration holds (2 - 3 days).

Cost: USD 8,000 - 16,000.

### 4.2 Bank connectivity reliability

- Plaid webhooks. Register SYNC_UPDATES_AVAILABLE webhooks so transactions update when the bank pushes changes, not only on manual sync. Add webhook signature verification. This is a P1 because users will otherwise see stale balances daily (4 - 6 days).

- Automated daily sync for all users via a scheduled job (Vercel Cron) with per-item backoff on Plaid rate limits (3 - 5 days).

- Sync status and error surface. Show “Last synced” errors and a retry affordance; surface Plaid error codes (ITEM_LOGIN_REQUIRED etc.) with actionable messages (3 - 5 days).

- Reconciliation check. A nightly job that cross-checks fetched totals so silent sync failures are caught (2 - 4 days).

- Legacy cleanup. Rename the Teller-era schema fields (tellerToken / tellerAccountId / tellerId) to Plaid names and remove Teller references from the landing page. Done. Fields renamed to accessToken / plaidAccountId / plaidTransactionId and the landing page now references Plaid. A final sweep for leftover Teller calls is advised (0 - 1 days).

Cost: USD 6,000 - 11,000.

### 4.3 Mobile store readiness

- Release signing. Configure Android release keystore and iOS signing; replace the debug-only CI build (1 - 2 days).

- App icons, splash screens, and store screenshots for Play Console and App Store (design USD 500 - 3,000).

- Store listings (title, description, category, screenshots, release notes) (1 - 2 days).

- Data-safety / privacy nutrition labels matching the privacy policy (1 - 2 days).

- Play Console closed testing track (beta testers) then production; App Store TestFlight.

- Deep linking. Configure Capacitor deep links for verify/reset email links so the native app opens them (2 - 3 days).

Cost: USD 1,500 - 6,000 (including design) plus the Apple Developer Program USD 99/year and Google Play USD 25 one-time.

### 4.4 AI reliability and cost control

- Token/cost budgets. Cap analysis runs per user per day; estimate token consumption; add a kill switch and caching improvements. The 1-hour insight cache already exists; extend it (3 - 4 days).

- PII and prompt hygiene. Confirm transaction data is minimized before it reaches Claude; log usage without logging raw data (2 - 3 days).

- Hallucination guardrails. Add a “verify with source data” footer to AI claims; every claim links to the underlying transactions or a cached number (3 - 4 days).

- Fallback telemetry. Track how often the local fallback engine is used so the team knows when Claude is down (1 - 2 days).

Cost: USD 4,000 - 7,000.

### 4.5 Support and feedback

- In-app support. Help centre, contact form, or Intercom-style widget (USD 0 - 89/month; effort 2 - 3 days).

- Feedback loop. Structured in-app feedback with opt-in diagnostics (2 - 3 days).

- Shared support inbox and a weekend SLAs policy. For a small team, a support tool like Crisp/Intercom from USD 0 - 25/month.

- Status page (Vercel status or free tier of a provider) (half day).

Cost: USD 1,500 - 4,000 plus USD 0 - 114/month tooling.

### 4.6 P1 cost summary

| Item | Cost |
| --- | --- |
| Automated testing + CI + load test | USD 8,000 - 16,000 |
| Bank connectivity reliability | USD 6,000 - 11,000 |
| Mobile store readiness | USD 1,500 - 6,000 |
| AI reliability and cost control | USD 4,000 - 7,000 |
| Support and feedback | USD 1,500 - 4,000 |

P1 subtotal: approximately USD 21,000 - 44,000.

## 5. P2: Required within 12 months of launch

- Multi-currency and exchange-rate features are partially built. Complete account-level FX handling and clearly label display conversions vs. real converted balances (4 - 6 days).

- Budget notifications and alert delivery. Make bill reminders, overspend alerts, and goal progress deterministic (scheduled jobs + push/web) (5 - 8 days).

- Household accounts. The schema exists; complete invitation flows, permissions, and shared budget visibility (6 - 10 days).

- Credit score and investments data need a live provider (or clearly labelled manual entry) or they read as unfinished surfaces (5 - 8 days).

- Receipt storage. Receipts are stored as raw blobs in the database; move to object storage (S3-compatible) and keep the DB for metadata (3 - 5 days).

- Performance work. Paginate transactions, virtualize long lists, and add an index check for large users (3 - 5 days).

- Accessibility pass. WCAG 2.1 AA: colour contrast, focus states, screen-reader labels, and reduced-motion verification (4 - 6 days).

- Localisation foundation. Internationalize strings and date/currency formats; launch in English only but architect for i18n (4 - 6 days).

P2 estimated cost: USD 15,000 - 30,000.

## 6. P3: Recommended growth and resilience

- Referral and invite programme (5 - 8 days).

- Monthly email digest of spending (5 - 8 days).

- A/B testing framework for onboarding and dashboard (3 - 5 days).

- Advanced fraud detection signals on unusual logins (IP/device) (4 - 6 days).

- Disaster recovery plan and multi-region option (2 - 4 days + infrastructure).

- Annual security review (ongoing USD 2,000 - 8,000/year).

P3 estimated cost: USD 8,000 - 18,000.

## 7. What is already done well

- Password hashing with bcrypt cost factor 12.

- AES-256-GCM encryption of bank tokens at rest with an explicit key-length guard.

- Email verification gate on all dashboard routes via middleware.

- Zod validation on API inputs.

- A deterministic local AI fallback so the assistant works without the Claude API.

- Cached AI insights (1-hour TTL) reducing cost and latency.

- Pull-to-refresh, haptics, and mobile-first layouts in the native wrapper.

- CI workflow that builds APK/IPA artifacts.

## 8. What is NOT present and needs building first (short list)

The following are the highest-leverage items. Everything else in this document can follow.

- Legal (ToS, Privacy Policy, DPA, disclosures).

- Rate limiting on auth and AI endpoints.

- Managed database backups + point-in-time recovery.

- Error monitoring (Sentry) and structured logging.

- Plaid webhooks + automated daily sync.

- Data export and account deletion.

- Automated test suite and CI test stage.

- Release-signed mobile builds.

- Security headers and a WAF/DDoS layer.

- Audit log.

## 9. Suggested 16-week launch roadmap

| Weeks | Focus | Deliverable |
| --- | --- | --- |
| 1 - 2 | Legal + security foundations | ToS, Privacy Policy, DPA, disclosures; external rate-limiting store; WAF/DDoS layer; secrets vault |
| 3 - 4 | Data and privacy engineering | Export, deletion, retention, erasure automation, AI prompt hygiene |
| 5 - 6 | Infrastructure | Managed DB with PITR, Sentry, logging, alerting, staging, CI guardrails |
| 7 - 8 | Bank reliability | Plaid webhooks, scheduled sync, error surfacing, reconciliation, schema cleanup |
| 9 - 10 | Testing | Unit, integration, E2E, load; CI test stage |
| 11 - 12 | AI hardening + cost control | Budgets, guardrails, fallback telemetry |
| 13 - 14 | Mobile store readiness | Signing, icons, store listings, TestFlight + Play closed track |
| 15 | Support + feedback | Help centre, status page, feedback loop |
| 16 | Pen test + go/no-go review | External pen test, fix criticals, launch controlled beta |

## 10. Operating cost estimate (monthly, post-launch)

| Item | Cost per month |
| --- | --- |
| Hosting: Vercel Pro | USD 20 |
| Database: managed Postgres (Neon/RDS) | USD 19 - 120 |
| Monitoring: Sentry + uptime + logs | USD 0 - 91 |
| Plaid production | USD 0 - 1,500 (usage-based; see note) |
| Anthropic Claude | USD 0 - 500 (usage-based; see note) |
| Email (SMTP) | USD 0 - 20 |
| Push notifications | USD 0 |
| Support tool (Intercom/Crisp) | USD 0 - 114 |
| Apple Developer Program | USD 8 (annual USD 99) |
| Object storage (receipts) | USD 0 - 10 |
| Total | USD 50 - 2,400 + variable Plaid/AI |

Notes on variable costs - Plaid charges per end user per month when the item connects to production data. Pricing is account- and market-dependent and typically in the range of USD 0.50 - 2.00 per user per month. At 500 users this is roughly USD 250 - 1,000/month. Confirm current pricing on Plaid’s website. - Claude costs depend on transaction volume and analysis frequency. With a 1-hour cache, a budget cap of a few analysis runs per user per day, and the local fallback, expect roughly USD 0.10 - 1.00 per active user per month at current token pricing. At 500 active users this is USD 50 - 500/month. - Worst-case realistic month (500 users): USD 350 - 2,400 plus your Plaid commitment.

## 11. Costing assumptions

- Engineering rate of USD 400/day (full-time senior or agency equivalent) unless noted otherwise.

- Legal is billed per engagement; figures are typical ranges for a startup fintech firm, not quotes.

- Plaid and Anthropic pricing are usage-based and change over time; figures are planning estimates, confirm before budgeting.

- Effort figures assume one engineer; the calendar duration of the 16-week roadmap assumes 2 engineers working in parallel on independent tracks (e.g. legal/security vs. infrastructure vs. bank connectivity).

## 12. Decision checklist

Before the first real user signs up, all of the following must be yes:

- ☐ ToS, Privacy Policy, and AI disclosures published and linked from signup.

- ☐ Rate limiting active on auth and AI endpoints.

- ☐ Database has point-in-time recovery and verified restore drills.

- ☐ Sentry and uptime alerts are firing on staging.

- ☐ Data export and account deletion work end to end.

- ☐ Plaid webhooks and scheduled daily sync are live in production.

- ☐ CI blocks merges on failed tests.

- ☐ Mobile builds are release-signed and store-ready.

- ☐ Penetration test completed and critical findings resolved.

- ☐ A human receives support emails and a status page exists.